## Gnatt Chart
Project Gantt Chart
Tray it Forward
Date in Question (apply highlight manually)
# | Task Description | Responsible | Status | Start Date | End Date | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16 | 2022-07-23 | 2022-07-30 | 2022-08-06 | 2022-08-13 | 2022-08-20 | 2022-08-27 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-24 | 2022-10-01 | 2022-10-08 | Comments | Status Legend (drop down menu):
1 | Project Overview |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [29 empty] | C | Complete
Determine boundaries on number of Trays/Seeds
1.01 | Timeline (Starts with Distrubution Day and works backwards from there) |  | i | 2022-01-01 | 2022-07-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [16 empty] | D | Delayed
1.02 | Partnership formulation (FEED Kearsarge [KNP, KFH, CSC, Spring Ledge, NLH, Food Pantries, Main Street Warner, Warner Market]) |  | c | 2022-01-01 | 2022-01-15 | 1 | 1 | 1 | [39 empty] | including defining roles
Assign Roles
1.03 | Meeting schedule (meet in 2 weeks; then monthly -> March then more frequently) (smaller teams) |  |  | 2022-01-01 | 2022-01-15 | 1 | 1 | 1 | [39 empty] | meeting schedule- who should be at the table, time, meeting location, schedule meetings out | I | In Process
1.04 | Registration |  | i | 2022-04-01 | 2022-05-15 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [23 empty] | P | Planned
1.05 | Tray Delivery Day | [46 empty] | historically this has been the Wednesday before Memorial Day. |  | Unknown
1.06 | Supply Donations (shovels, gloves, trowels, etc.)
1.07 | Debrief |  |  | 2022-06-01 | 2022-06-15 | [21 empty] | 1 | 1 | 1
1.08
2 | Promotion (Getting the Word out) |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
2.01 | Define service area (Andover, Sunapee, Kearsarge School regions: Abenaki, Henniker, Newport, Hannaford Employees, Danbury) (Survey past recipients to "pre-register") |  |  | 2022-01-01 | 2022-02-01 | 1 | 1 | 1 | 1 | 1
2.02 | Define promotional channels (KNP Primary promotional channel - possible secondary marketing channels - KFH, NLH, Warner Connects, Food Pantries, Food Banks) Determine Food Pantry/Bradford Elementary School/Epiphany Interest/Cap |  |  | 2022-02-01 | 2022-02-15 |  |  |  |  | 1 | 1 | 1
2.03 | Website/Social Media Development/Spring Ledge Website |  |  | 2022-02-01 | 2022-04-01 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.04 | Print/Ad flyer development (insert 4 new line (tray sponsoring/fund raising)) Promo activities (e.g. ads in the shopper/intertown article) |  | i | 2022-02-01 | 2022-04-22 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.05 | Draft Email for Tray Recipient registration |  |  | 2022-02-01 | 2022-04-01 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.06 | Draft email for volunteer day delivery day reminder |  |  | 2022-04-01 | 2022-05-01 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [24 empty] | to be sent week before delivery & day of delivery
Draft email for recipient delivery day reminder
2.07 | Develop Individual Distribution Route and Contact Instrutions for volunteers |  |  | 2022-02-15 | 2022-03-15 | [6 empty] | 1 | 1 | 1 | 1 | 1
2.08 | Info kits to accompany trays |  |  | 2022-03-01 | 2022-04-15 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.09 | Create lists of last year's recipients in order to offer early tray registration |  |  | 2022-02-01 | 2022-04-01 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.1 | Phone/E-mail past recipients for early registration (Arrange Phone Tree) |  |  | 2022-04-01 | 2022-04-15 | [12 empty] | 1 | 1 | 1
2.11 | Start Open Registration |  |  | 2022-04-16 | 2022-05-11 | [14 empty] | 1 | 1 | 1 | 1 | 1
2.12 |  |  |  | 2022-04-01 | 2022-04-15 | [12 empty] | 1 | 1 | 1
2.13 |  |  |  | 2022-05-18 | 2022-05-21 | [19 empty] | 1 | 1
2.14
2.15
3 | Website Registration Form and Table |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
3.01 | Airtable Development |  |  | 2022-02-01 | 2022-03-01 |  |  |  |  | 1 | 1 | 1 | 1 | 1
3.02 | Airtable Live Date |  |  | 2022-04-01 | 2022-04-01 | [12 empty] | 1
3.03 | Airtable Close Date |  |  | 2022-05-18 | 2022-05-18 | [19 empty] | 1
3.04 | Create Master List of Recipients |  |  | 2022-05-20 | 2022-05-20 | [19 empty] | 1
3.05
4 | Tray Distribution |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
4.01 | Define Volunteer Tray pick up processes |  |  | 2022-05-01 | 2022-05-18 | [17 empty] | 1 | 1 | 1
4.02 | Schedule Volunteer pick up times |  |  | 2022-05-21 | 2022-05-21 | [19 empty] | 1 | 1
4.03 | Compost volunteers and bagging schedule |  |  | 2022-05-01 | 2022-05-21 | [17 empty] | 1 | 1 | 1 | 1
4.04 | Arrange Compost Donor |  |  | 2022-05-01 | 2022-05-07 | [17 empty] | 1 | 1
4.05 | Acquire compost bags |  |  | 2022-05-01 | 2022-05-07 | [17 empty] | 1 | 1
4.06 | Compost bagging day (5/21) |  |  | 2022-05-14 | 2022-05-21 | [18 empty] | 1 | 1 | 1
4.07 | Arrange Supply Donations |  |  | 2022-04-01 | 2022-04-30 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1
4.08
4.09 | Literature (growing guide, flyer for community education, container growing guide) to be delivered along with trays |  |  | 2022-04-15 | 2022-05-18 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1
4.1 | Assign Tray Distribution Day Roles to Volunteers |  |  | 2022-05-22 | 2022-05-22 | [20 empty] | 1
4.11 | Positioning Respources for Distribution Day |  |  | 2022-05-19 | 2022-05-19 | [19 empty] | 1
5 | Farmers |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
5.01 | Tray & Seed Composition |  |  | 2022-02-23 | 2022-02-23 | [7 empty] | 1
5.02 | Tray Sizes (Label trays front-back) |  |  | 2022-02-23 | 2022-02-23 | [7 empty] | 1 | [34 empty] | 6-packs x4=24 plants for large garden tray, 2 6-packs=12 plants for small garden tray
5.03 | How many trays/seeds | [46 empty] | 24 plants per tray= 300, 12 plants per tray=100
5.04 | 1st sowing |  | i | 2022-03-01 | 2022-04-25 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Plugs to transplant on 04/25/2022, Leeks, Yellow Onions, Red Onions |  | p | 2022-04-25 | 2022-04-25 | [16 empty] | 1
5.05 | 2nd sowing |  | i | 2022-03-15 | 2022-04-25 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Plugs to transplant on 04/25/2022, Pepper Snacking, Pepper Bell, Pepper Jalapeno, Eggplant Back Bell |  | P | 2022-04-25 | 2022-04-25 | [16 empty] | 1
5.06 | 3rd sowing |  | i | 2022-04-01 | 2022-04-25 | [12 empty] | 1 | 1 | 1 | 1 | 1
| Plugs to transplant on 04/25/2022, Tomato big beef slicer, tomator early girl, tomator paste, sweet million, basil genovese, marigold lemon gem |  | P | 2022-04-25 | 2022-04-25 | [16 empty] | 1
5.07 | 4th sowing |  | P | 2022-04-15 | 2022-04-25 | [14 empty] | 1 | 1 | 1
| Plugs to transplant on 04/25/2022, Dill, Kale red Russian, Broccoli, Lettuce green, Lettuce red, lettuce mix |  | P | 2022-04-25 | 2022-04-25 | [16 empty] | 1
5.08 | 5th sowing- Direct seed into 6-pack, cucke compact, cuke slicer, winter squash butternut, winter squash delicata, summer squash yellow, zucchini, green beans |  | P | 2022-04-25 | 2022-04-25 | [16 empty] | 1
5.09 | Plants to be ready |  | P | 2022-05-25 | 2022-05-25 | [20 empty] | 1
6 | Post Distribution |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
6.01 | Victory Garden Support Group/Facebook
6.02 | Surveying & Feedback (Leon's class) |  |  | 2022-10-01 | 2022-10-15 | [39 empty] | 1 | 1 | 1
6.03 | Superlatives Contest
6.04 | Weekly Gardening Newsletters
6.05 | Garden Workshops (Gardening 101)
6.06 | CSC Demo Garden for tutorials
6.07 | Container Gardening tutorial
6.08
6.09
6.1
6.11
6.12
6.13
6.14
6.15
6.16
6.09
6.1
6.11
[5 empty] | Active Tasks | 4 | 4 | 4 | 2 | 8 | 7 | 8 | 9 | 9 | 8 | 9 | 8 | 15 | 11 | 14 | 11 | 15 | 10 | 9 | 11 | 7 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1